## Resource loading (hidden)
[5 empty] | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30
Role | Location |  | Unit | Assigned Role | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Weeks | Hrs/ day | Hrs | Rate per hour in USD | Total Amount
TBD | Onsite | Malawi | DNA05 | Onsite- Data Science Lead (JL 6) | [12 empty] | 4 | 8 | 160 | 150 | 24000 | bar: 2018-05-14 to 2018-07-30
TBD | Offshore | India | DNA05 | Offshore - Senior Principal (JL7) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 8.8 | 52.8 | 75 | 3960
TBD | Offshore | India | DNA05 | Offshore - Data Science Lead (JL 6) | [12 empty] | 8 | 8.8 | 352 | 50 | 17600 | bar: 2018-05-14 to 2018-05-28; 2018-07-02 to 2018-07-30
TBD | Offshore | India | DNA05 | Offshore - Data Analyst (JL 4B) |  |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 8.8 | 704 | 32 | 22528
68088
Note on I4: Swetapadma Paricha Patnaik: Malawi Travel. This may be split into two trips of 2 weeks

## Activity_Task_Deliverables (hidden)
Activity | Task | Deliverables
Data Understanding & Assessment | Understand business process | Data quality report
| Understand Data | Finalized Data dictionary
Understand sources of data
Understand structure of data
Validate data quality
Perform descriptive analysis
Exploratory Data Analysis (EDA) | Data preparation: Clean, merge and transform | EDA report
Perform data analysis (including univariate & bivariate analysis)
Model feasibility assessment | Review data quality and analysis reports to establish feasibility of model development | Analytical Model Feasibility Assessment report
| Create Model Development proposal | Model Development proposal

## High Level Plan
| 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30
Activity | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12
Project Preparatory Work | bar: 2018-05-14 to 2018-05-21
Data Understanding & Assessment | bar: 2018-05-28 to 2018-06-04
Exploratory Data Analysis (EDA) | bar: 2018-06-11 to 2018-07-02
Model feasibility assessment | bar: 2018-07-02 to 2018-07-30

## Detailed Plan
| 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30
Activities / Tasks | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12
Project Preparatory Work | bar: 2018-05-14 to 2018-05-21
Understand the use case and its objectives | bar: 2018-05-14
Elaborate the use case | bar: 2018-05-14 to 2018-05-21
Identify the approach for the use case execution | bar: 2018-05-21
Identify data requirements | bar: 2018-05-21
Identify sources of data (i.e. MNO, UNICEF, Health care / facilities in Malawi, Facebook and World pop) | bar: 2018-05-21
Perform resource mobilization | bar: 2018-05-21
Data Understanding & Assessment | bar: 2018-05-28 to 2018-06-04
Understand data dictionary | bar: 2018-05-28 to 2018-06-04
Understand Data - MNO | bar: 2018-05-28 to 2018-06-04
Understand Data - UNICEF | bar: 2018-05-28 to 2018-06-04
Understand Data - health care system in Malawi | bar: 2018-05-28 to 2018-06-04
Understand Data - List of health facilities in Malawi | bar: 2018-05-28 to 2018-06-04
Understand Data - Facebook data | bar: 2018-05-28 to 2018-06-04
Understand Data - World pop data | bar: 2018-05-28 to 2018-06-04
Assess Data Quality | bar: 2018-06-04
Exploratory Data Analysis (EDA) | bar: 2018-06-11 to 2018-07-02
Perform descriptive analytics | bar: 2018-06-11 to 2018-06-18
Data preparation: Clean, merge and transform | bar: 2018-06-11 to 2018-06-18
Treatment of data- missing, outliers, etc. | bar: 2018-06-11 to 2018-06-18
Feature Engineering | bar: 2018-06-11 to 2018-06-18
Exploratory Analysis | bar: 2018-06-11 to 2018-07-02
Perform EDA visualization | bar: 2018-06-25 to 2018-07-02
Prepare EDA report | bar: 2018-07-02
Model feasibility assessment | bar: 2018-07-02 to 2018-07-30
Review the data availability and sufficiency for modeling | bar: 2018-07-02 to 2018-07-09
Assess the variables /attributes for modeling | bar: 2018-07-09 to 2018-07-16
Finalize modeling approach | bar: 2018-07-16 to 2018-07-23
Create and finalize Model Development proposal | bar: 2018-07-23 to 2018-07-30