## Detailed Plan (hidden)
| 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05
Activities / Tasks | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
Analyze sample MNO data | bar: 2018-08-06
Define MNO data aggregation rules | bar: 2018-08-13 to 2018-08-20
Understand and write Neo4j script for establishing relation between unique mobile numbers | bar: 2018-08-13 to 2018-08-20
Understand and prepare extract from Facebook High Resolution Settlement Layer file and Administrative shapefiles | bar: 2018-08-13 to 2018-08-20
Understand and update data dictionary | bar: 2018-08-20
Analyze triangulation of population and health data with MNO data | bar: 2018-08-20 to 2018-08-27
Build MNO data aggregation and EDA scripts in Python | bar: 2018-08-13 to 2018-08-27
Exploratory Data Analysis (EDA) | bar: 2018-09-03 to 2018-10-15
Perform descriptive analytics on MNO data | bar: 2018-09-03 to 2018-09-10
Data preparation: Clean, merge and transform | bar: 2018-09-03 to 2018-09-10
Treatment of data- missing, outliers, etc. | bar: 2018-09-03 to 2018-09-10
Data quality checks | bar: 2018-09-03 to 2018-09-10
Prepare data quality report of MNO data | bar: 2018-09-10
Get extract from MNO data using Python script (aggregation rules) | bar: 2018-09-10 to 2018-09-24
Run Neo4j script to get relation established among unique mobile numbers | bar: 2018-09-10 to 2018-10-08
Perform EDA on extracted MNO data (Python) | bar: 2018-09-10 to 2018-10-08
Prepare EDA report | bar: 2018-10-08 to 2018-10-15
Model feasibility assessment | bar: 2018-10-15 to 2018-11-05
Review the data availability and sufficiency for modeling | bar: 2018-10-15 to 2018-10-22
Assess the variables /attributes for modeling | bar: 2018-10-22 to 2018-10-29
Finalize modeling approach | bar: 2018-10-29
Create and finalize Model Development proposal | bar: 2018-10-29 to 2018-11-05
Assumptions | bar: 2018-08-06 to 2018-08-20
1. EDA dataset will be made available latest by 27-August, 2018
2. All Infrastructure required for EDA will be made available latest by 27-August, 2018
3. Any delays in data set availability or infrastructure readiness may lead to an extension of EDA timelines to be managed through a Change Request

## Foundation Approach - Plan
|  | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31
Activities / Tasks | Deliverables | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
7 days of sample MNO data analysis/EDA | - Data quality report (MNO) - Exploratory Data Analysis (EDA) report
Test daily aggregation scripts | bar: 2018-10-01
Perform Data Quality Checks & Prepare Data quality report | bar: 2018-10-01
Develop/finalize MNO daily data aggregation Python scripts | bar: 2018-10-01 to 2018-10-08
Execute MNO data aggregation and EDA scripts in Python | bar: 2018-10-01 to 2018-10-08
Exploratory Data Analysis (EDA) on 26 months data | - Data quality report (MNO) - Exploratory Data Analysis (EDA) report
Develop/finalize MNO monthly data aggregation Python scripts | bar: 2018-10-15 to 2018-10-22
Perform Data Quality Checks, Missing Value Treatment & Prepare Data quality report | bar: 2018-10-15 to 2018-10-29
Execute MNO data aggregation and EDA scripts in Python | bar: 2018-10-15 to 2018-11-05
Perform descriptive analytics on aggregated data | bar: 2018-10-29 to 2018-11-05
Population density mapping | Population density mapping with mobile call density for 2016 and 2017. Population density projection factoring exponential growth from 2019 - 23 | bar: 2018-11-05 to 2018-11-19
Estimate the power law relationship between CDR call density and population density at ADM unit level using regression analysis | bar: 2018-11-05 to 2018-11-19
Short Term Population Movement Analysis | - Most visited trajectories per Administrative unit - Most frequently visited stay point per Administrative unit | bar: 2018-11-19 to 2018-12-03
Analyze short term movements at individual and aggregated levels to identify points of interest within an ADM unit | bar: 2018-11-19 to 2018-12-03
Long Term Population Movement Analysis | Monthly Inflow/Outflow of population movement at Administraive unit level - User Manual for EDA / visualization dashboards | bar: 2018-12-03 to 2018-12-17
Analyze and estimate monthly population movement by netflows and proportion of inflow/outflow at ADM unit level | bar: 2018-12-03 to 2018-12-17
Model feasibility assessment | - Model feasibility assessment report (Technical report will be consolidation of EDA report and Model feasibility assessment report)
Assess the variables /attributes for modeling | bar: 2018-12-17
Review the data availability and sufficiency for optimization modeling | bar: 2018-12-17 to 2018-12-24
Finalize optimization modeling approach & plan | bar: 2018-12-24 to 2018-12-31
Assumptions | bar: 2018-10-01 to 2018-10-15
1. 7 days of sample CDR data will be made available latest by 3-October 2018
2. All Infrastructure required for EDA will be made available latest by 3-October 2018
3. All 26 month EDA dataset will be made available latest by 15-October 2018
4. All 26 months of CDR data will be used for population density mapping
5. Last three month of data will be considered for Short Term Population Movement Analysis
6. All 26 months of data will be used for Long term population movement analysis
7. Any delays in data set availability or infrastructure readiness may lead to an extension of EDA timelines to be managed through a Change Request
8. Fixed effect factor is assumed to be available for the same duration as CDR data