## Resource loading (hidden)
[5 empty] | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30
Role | Location |  | Unit | Assigned Role | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Weeks | Hrs/ day | Hrs | Rate per hour in USD | Total Amount
TBD | Onsite | Malawi | DNA05 | Onsite- Data Science Lead (JL 6) | [12 empty] | 4 | 8 | 160 | 150 | 24000 | bar: 2018-05-14 to 2018-07-30
TBD | Offshore | India | DNA05 | Offshore - Senior Principal (JL7) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 8.8 | 52.8 | 75 | 3960
TBD | Offshore | India | DNA05 | Offshore - Data Science Lead (JL 6) | [12 empty] | 8 | 8.8 | 352 | 50 | 17600 | bar: 2018-05-14 to 2018-05-28; 2018-07-02 to 2018-07-30
TBD | Offshore | India | DNA05 | Offshore - Data Analyst (JL 4B) |  |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 8.8 | 704 | 32 | 22528
68088
Note on I4: Swetapadma Paricha Patnaik: Malawi Travel. This may be split into two trips of 2 weeks

## Activity_Task_Deliverables (hidden)
Activity | Task | Deliverables
Data Understanding & Assessment | Understand business process | Data quality report
| Understand Data | Finalized Data dictionary
Understand sources of data
Understand structure of data
Validate data quality
Perform descriptive analysis
Exploratory Data Analysis (EDA) | Data preparation: Clean, merge and transform | EDA report
Perform data analysis (including univariate & bivariate analysis)
Model feasibility assessment | Review data quality and analysis reports to establish feasibility of model development | Analytical Model Feasibility Assessment report
| Create Model Development proposal | Model Development proposal

## Detailed Plan
| 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05
Activities / Tasks | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
Analyze sample MNO data | bar: 2018-08-06
Define MNO data aggregation rules | bar: 2018-08-13 to 2018-08-20
Understand and write Neo4j script for establishing relation between unique mobile numbers | bar: 2018-08-13 to 2018-08-20
Understand and prepare extract from Facebook High Resolution Settlement Layer file and Administrative shapefiles | bar: 2018-08-13 to 2018-08-20
Understand and update data dictionary | bar: 2018-08-20
Analyze triangulation of population and health data with MNO data | bar: 2018-08-20 to 2018-08-27
Build MNO data aggregation and EDA scripts in Python | bar: 2018-08-13 to 2018-08-27
Exploratory Data Analysis (EDA) | bar: 2018-09-03 to 2018-10-15
Perform descriptive analytics on MNO data | bar: 2018-09-03 to 2018-09-10
Data preparation: Clean, merge and transform | bar: 2018-09-03 to 2018-09-10
Treatment of data- missing, outliers, etc. | bar: 2018-09-03 to 2018-09-10
Data quality checks | bar: 2018-09-03 to 2018-09-10
Prepare data quality report of MNO data | bar: 2018-09-10
Get extract from MNO data using Python script (aggregation rules) | bar: 2018-09-10 to 2018-09-24
Run Neo4j script to get relation established among unique mobile numbers | bar: 2018-09-10 to 2018-10-08
Perform EDA on extracted MNO data (Python) | bar: 2018-09-10 to 2018-10-08
Prepare EDA report | bar: 2018-10-08 to 2018-10-15
Model feasibility assessment | bar: 2018-10-15 to 2018-11-05
Review the data availability and sufficiency for modeling | bar: 2018-10-15 to 2018-10-22
Assess the variables /attributes for modeling | bar: 2018-10-22 to 2018-10-29
Finalize modeling approach | bar: 2018-10-29
Create and finalize Model Development proposal | bar: 2018-10-29 to 2018-11-05
Assumptions | bar: 2018-08-06 to 2018-08-20
1. EDA dataset will be made available latest by 3-September 2018
2. All Infrastructure required for EDA will be made available latest by 3-September, 2018
3. Any delays in data set availability or infrastructure readiness may lead to an extension of EDA timelines to be managed through a Change Request