## Detailed plan-Week-wise
[6 empty] | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25
Activities / Tasks | Planned Start Date | Planned End Date | Estimated End Date | Status | Deliverables | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12
Identification of probable location of new health posts |  |  |  |  | - Population forecast for 2019-23 - Probable location of new health posts for 2019-23
Create and finalize approach for identification of probable location of new health posts | 2019-01-07 | 2019-01-14 |  | Completed | bar: 2019-01-07 to 2019-01-14
Create and finalize plan for identification of probable location of new health posts project | 2019-01-14 | 2019-01-18 |  | Completed | bar: 2019-01-14
Population forecast for the next five years (2019 -23) | 2019-01-16 | 2019-01-22 |  | Completed | bar: 2019-01-14 to 2019-01-21
Calibrate α value (power equation) using the World pop population and the estimated population for the year 2016 from phase-1 of Malawi usecase |  |  |  | In progress | bar: 2019-01-14 to 2019-01-21
Calculate call density @ TA level for the year 2018-22 using call desnity growth rate for the years 2016 and 2017 |  |  |  | In progress | bar: 2019-01-14 to 2019-01-21
Estimate population density @ TA level using Power equation of Phase-1 of Malawi Usecase |  |  |  | In progress | bar: 2019-01-14 to 2019-01-21
Compute total population @ TA level |  |  |  | In progress | bar: 2019-01-14 to 2019-01-21
Get Uncovered area and uncovered population | 2019-01-23 | 2019-02-01 |  | Completed | bar: 2019-01-21 to 2019-01-28
Use UNICEF catchment shape file to get uncovered area and uncovered population for the year 2019 | bar: 2019-01-21 to 2019-01-28
Get uncovered population for next four years, for new health post locations using circle of 5 km radius around health posts | bar: 2019-01-21 to 2019-01-28
Distribution of the forecasted population for the years 2019 -23 | 2019-01-23 | 2019-02-01 |  | Completed | bar: 2019-01-21 to 2019-01-28
Overlay grid (eg:1 sqkm) on worldpop rasterfile and calculate the % of population in each grid | bar: 2019-01-21 to 2019-01-28
Perform distribution of estimated population @ TA level | bar: 2019-01-21 to 2019-01-28
Formation of Clusters for the forecasted population | 2019-02-04 | 2019-02-22 |  | Completed | bar: 2019-02-04 to 2019-02-18
Find centroid of each grid | bar: 2019-02-04 to 2019-02-18
Find clusters for the cluster grids for the entire catchment population (Cj) | bar: 2019-02-04 to 2019-02-18
Overlay existing health posts file over the cluster year wise | bar: 2019-02-04 to 2019-02-18
Map clusters to the nearest health post year on year | bar: 2019-02-04 to 2019-02-18
Identify the clusters of uncovered population (Popu) and determine the demand points year on year | bar: 2019-02-04 to 2019-02-18
Calculate weights for the objective function @ TA level | 2019-02-25 | 2019-03-01 |  | Completed | bar: 2019-02-25
Select all existing health posts and candidates for new probable health post locations | 2019-03-04 | 2019-03-15 |  | Completed | bar: 2019-03-04 to 2019-03-11
Obtain the location of new health posts year on year (2019-23) using demand points, facilities and impedance (a distance beyond which a patient cannot travel to the health post, i.e. 5 km) | 2019-03-15 | 2019-03-19 |  | Completed | bar: 2019-03-18
Validate the location of new health posts with DIAL, C/S and MOH Malawi | 2019-03-19 | 2019-03-22 |  | Completed | bar: 2019-03-18
Finalize location of new health posts | 2019-03-20 | 2019-03-22 |  | Completed | bar: 2019-03-18
PowerBI reports for health posts location |  |  |  |  | - PowerBI report on health posts location | bar: 2019-03-18 to 2019-03-25
Show location of current health posts on Malawi Map | 2019-03-18 | 2019-03-26 |  | Completed | bar: 2019-03-18 to 2019-03-25
Show probable location of new health posts on Malawi Map | 2019-03-18 | 2019-03-26 |  | Completed | bar: 2019-03-18 to 2019-03-25
Review and finalize PowerBI report for probable location of new health posts on Malawi Map | 2019-03-25 | 2019-03-29 |  | Completed | bar: 2019-03-25

## Resource loading (hidden)
[5 empty] | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25
Role | Location |  | Unit | Assigned Role | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | # of Weeks | Hrs/day | Total Hrs | Rate/hr (USD) | Total Amount
| Onsite | Malawi | DNA05 | Onsite- Data Science Lead (JL 6) | [12 empty] | 0 | 8 | 0 | 150 | 0
| Offshore | India | DNA05 | Analytics Practice Head | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | 1.8 | 8.8 | 80 | 75 | 6000
| Offshore | India | DNA05 | Offshore - Project Manager (JL6) | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.4 | 8.8 | 105.6 | 75 | 7920
| Offshore | India | DNA05 | Offshore - Data Science Lead (JL 6) | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 9.6 | 8.8 | 422.4 | 50 | 21120
| Offshore | India | DNA05 | Offshore - Data Analyst (JL 4B) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 8.8 | 1056 | 32 | 33792
| Onsite | Malawi | DNASURE | Technology Architect | [12 empty] | 0 | 8 | 0 | 108 | 0
| Offshore | India | DNASURE | Technology Architect | [12 empty] | 0 | 8.8 | 0 | 45 | 0
| Offshore | India | DNASURE | Technology Lead | [12 empty] | 0 | 8.8 | 0 | 34 | 0
| Offshore | India | DNASURE | Software Engineer | [12 empty] | 0 | 8.8 | 0 | 28 | 0
| Onsite | US | Consulting | Onsite- Program Lead (JL 6) | [12 empty] | 0 | 8 | 0 | 170 | 0
| Offshore | India | DNASURE | Offshore - Project manager | [12 empty] | 0 | 8.8 | 0 | 45 | 0
[20 empty] | Total | 68832
Jan Milestone | 24944 |  |  |  | 2019-01-07: 2019-01-07; 2019-01-14: 2019-01-14; 2019-01-21: 2019-01-21; 2019-01-28: 2019-01-28
Role | Location |  | Unit | Assigned Role | Wk1 | Wk2 | Wk3 | Wk4 | Weeks | Hrs/day | Hrs | Rate/hr (USD) | Total Amount
| Onsite | Malawi | DNA05 | Onsite- Data Science Lead (JL 6) | 2019-02-04: 0; 2019-02-11: 0; 2019-02-18: 0; 2019-02-25: 150; 2019-03-04: 0
|  |  | DNA05 | Analytics Practice Head | 0.2 | 0.2 | 0.1 | 0.1 | 0.6 | 8.8 | 26.4 | 75 | 2000
| Offshore | India | DNA05 | Offshore - Project Manager (JL6) | 0.2 | 0.2 | 0.2 | 0.2 | 0.8 | 8.8 | 35.2 | 75 | 2640
| Offshore | India | DNA05 | Offshore - Data Science Lead (JL 6) | 0.8 | 0.8 | 0.8 | 0.8 | 3.2 | 8.8 | 140.8 | 50 | 7040
| Offshore | India | DNA05 | Offshore - Data Analyst (JL 4B) | 2 | 2 | 2 | 2 | 8 | 8.8 | 352 | 32 | 11264
| Onsite | Malawi | DNASURE | Technology Architect | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 108; 2019-03-04: 0
| Offshore | India | DNASURE | Technology Architect | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 45; 2019-03-04: 0
| Offshore | India | DNASURE | Technology Lead | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 34; 2019-03-04: 0
| Offshore | India | DNASURE | Software Engineer | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 28; 2019-03-04: 0
| Onsite | US | Consulting | Onsite- Program Lead (JL 6) | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 170; 2019-03-04: 0
| Offshore | India | DNASURE | Offshore - Project manager | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 45; 2019-03-04: 0
Feb Milestone | 24944 |  |  |  | 2019-01-07: 2019-02-04; 2019-01-14: 2019-02-11; 2019-01-21: 2019-02-18; 2019-01-28: 2019-02-25
Role | Location |  | Unit | Assigned Role | Wk5 | Wk6 | Wk7 | Wk8 | Weeks | Hrs/day | Hrs | Rate/hr (USD) | Total Amount
| Onsite | Malawi | DNA05 | Onsite- Data Science Lead (JL 6) | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 150; 2019-03-04: 0
|  |  | DNA05 | Analytics Practice Head | 0.2 | 0.2 | 0.1 | 0.1 | 0.6 | 8.8 | 26.4 | 75 | 2000
| Offshore | India | DNA05 | Offshore - Project Manager (JL6) | 0.2 | 0.2 | 0.2 | 0.2 | 0.8 | 8.8 | 35.2 | 75 | 2640
| Offshore | India | DNA05 | Offshore - Data Science Lead (JL 6) | 0.8 | 0.8 | 0.8 | 0.8 | 3.2 | 8.8 | 140.8 | 50 | 7040
| Offshore | India | DNA05 | Offshore - Data Analyst (JL 4B) | 2 | 2 | 2 | 2 | 8 | 8.8 | 352 | 32 | 11264
| Onsite | Malawi | DNASURE | Technology Architect | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 108; 2019-03-04: 0
| Offshore | India | DNASURE | Technology Architect | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 45; 2019-03-04: 0
| Offshore | India | DNASURE | Technology Lead | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 34; 2019-03-04: 0
| Offshore | India | DNASURE | Software Engineer | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 28; 2019-03-04: 0
| Onsite | US | Consulting | Onsite- Program Lead (JL 6) | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 170; 2019-03-04: 0
| Offshore | India | DNASURE | Offshore - Project manager | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 45; 2019-03-04: 0
Mar Milestone | 24944 |  |  |  | 2019-01-07: 2019-03-04; 2019-01-14: 2019-03-11; 2019-01-21: 2019-03-18; 2019-01-28: 2019-03-25
Role | Location |  | Unit | Assigned Role | Wk9 | Wk10 | Wk11 | Wk12 | Weeks | Hrs/day | Hrs | Rate/hr (USD) | Total Amount
| Onsite | Malawi | DNA05 | Onsite- Data Science Lead (JL 6) | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 150; 2019-03-04: 0
|  |  | DNA05 | Analytics Practice Head | 0.2 | 0.2 | 0.1 | 0.1 | 0.6 | 8.8 | 26.4 | 75 | 2000
| Offshore | India | DNA05 | Offshore - Project Manager (JL6) | 0.2 | 0.2 | 0.2 | 0.2 | 0.8 | 8.8 | 35.2 | 75 | 2640
| Offshore | India | DNA05 | Offshore - Data Science Lead (JL 6) | 0.8 | 0.8 | 0.8 | 0.8 | 3.2 | 8.8 | 140.8 | 50 | 7040
| Offshore | India | DNA05 | Offshore - Data Analyst (JL 4B) | 2 | 2 | 2 | 2 | 8 | 8.8 | 352 | 32 | 11264
| Onsite | Malawi | DNASURE | Technology Architect | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 108; 2019-03-04: 0
| Offshore | India | DNASURE | Technology Architect | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 45; 2019-03-04: 0
| Offshore | India | DNASURE | Technology Lead | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 34; 2019-03-04: 0
| Offshore | India | DNASURE | Software Engineer | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 28; 2019-03-04: 0
| Onsite | US | Consulting | Onsite- Program Lead (JL 6) | 2019-02-04: 0; 2019-02-11: 8; 2019-02-18: 0; 2019-02-25: 170; 2019-03-04: 0
| Offshore | India | DNASURE | Offshore - Project manager | 2019-02-04: 0; 2019-02-11: 8.8; 2019-02-18: 0; 2019-02-25: 45; 2019-03-04: 0
Note on B16: Chitra Navin Dubey: 5% Analytics budget effort per month 2000 is added
Note on B30: Chitra Navin Dubey: 5% Analytics budget effort per month 2000 is added
Note on B44: Chitra Navin Dubey: 5% Analytics budget effort per month 2000 is added